## Summary
Myna Site
Sl. No. | Work Type | Order Value | Paid Amount | Balance to pay
1 | PO | 5399325.1614 | 5345450.99 | 53874.1714
2 | WO | 23926472.6504 | 20799860.128 | 3039292.5238
3 | Direct Payment | 2731924.4948 | 2731926.9 | -2.4052
Grand Total |  | 32057722.3066 | 28877238.018 | 3093164.29

## PO_Payments
Purchase Order Tracker - 2024 to 2025
[13 empty] | Payment Details | [6 empty] | Invoice Status |  |  |  | UTR Details
S.No | Submission Date | Order Type | Oder Ref No | Order Date | Budget No. | Supplier | Description | Order Value | Loading | Freight | Taxes | Total Amount | Advance 1 | Advance 2 | RA Bill 1 | RA Bill 2 | Final Bill | Total Paid | Balance to pay | Status | Date | Invoice No. | Amount | Date | UTR No. | Remarks
1 | 2025-04-10 | PO | AGN/PO/M-001/2025-26 | 09.Nov.2025 | 003 - 2024-25 | Nitin wires and meshes Pvt Ltd. | Supply of Nitin Trellis Stone 1205mm x 2410mm 5mm Thickness. | 92000 | 0 | 0 | 16560 | 108560 | 108560 |  |  |  |  | 108560 | 0 | Submitted | 17.04.2025 | 57603/2025-26 | 108560 |  |  | Original Invoice submitted on 15.07.2025 - Mail
2 | 2025-04-28 | PO | AGN/PO/M-002/2025-26 | 2025-04-28 | 014 - 2024-25 | Somani Ispat Private Limited | Supply of MS Pipes | 65371.25 | 0 | 0 | 11766.825 | 77138.075 | 77138 |  |  |  |  | 77138 | 0.075 | Not Submitted | [5 empty] | 100% Advance as per client approval
3 | 2025-04-28 | PO | AGN/PO/M-003/2025-26 | 2025-04-28 | 015 - 2024-25 | Innovative Multitech Solutions | Supply of MS Fabricated 300L Solat Tank | 85000 | 0 | 0 | 15300 | 100300 | 100300 |  |  |  |  | 100300 | 0 | Not Submitted | [5 empty] | 100% Advance as per client approval
4 | 2025-05-09 | PO | AGN/PO/M-027/2024-25 | 2024-12-30 | 224 - 2024-25 | Zeo Concept Pvt Ltd | Supply of furniture | 1525424.57 | 0 | 0 | 274576.4226 | 1800000.9926 | 1122525 | 677476 |  |  |  | 1800001 | -0.0074 | Submitted | 19.05.2025 | oi-000580 | 1154951.01 |  |  | Original Invoice submitted on 15.07.2025 - Mail
5 | 09-05-2025 and 21.08.2025 | PO | AGN/PO/M-004/2025-26 | 09.06.2025 | 038 - 2025-26 | Dastkari Designs Pvt Ltd | Supply of furniture | 737500 | 0 | 11000 | 132750 | 881250 | 652687.5 | 228562.5 |  |  |  | 881250 | 0 | Submitted | 30.08.2025 | 149 | 1211650 |  |  | Original invoice submitted - Invoice is mixing of two orders 004 and 006
6 | 2025-07-02 | PO | AGN/PO/M-005/2025-26 | 10.06.2025 | 052 - 2025-26 | Radha Krishna Granites & Tiles | Supply of Polished Granite | 34718.64 | 0 | 0 | 6249.3552 | 40967.9952 |  |  |  |  | 40968 | 40968 | -0.0048 | Submitted | 10.06.2025 | 13 | 40968 |  |  | Original Invoice submitted with client approval
7 | 09-05-2025 and 21.08.2025 | PO | AGN/PO/M-006/2025-26 | 08.07.2025 | 054 - 2025-26 | Dastkari Designs Pvt Ltd | Supply of Furniture | 280000 | 0 | 0 | 50400 | 330400 | 247800 |  |  |  | 82600 | 330400 | 0 | Submitted | 30.08.2025 | 149 | 1211650 |  |  | Original invoice submitted - Invoice is mixing of two orders 004 and 006
8 | 21.08.2025 | PO | AGN/PO/M-016/2025-26 | 01.08.2025 | 075 - 2025-26 | MVN Building Systems | Supply of Steel and roofing sheets | 161455.08 | 0 | 0 | 29061.9144 | 190516.9944 |  |  |  |  | 190517 | 190517 | -0.0056 | Submitted | 02.08.2025 | MNV/25-26/106 | 190517 |  |  | Original invoice submitted
9 | 21.08.2025 | PO | AGN/PO/M-017/2025-26 | 01.08.2025 | 073 - 2025-26 | Robo Gates India Pvt Ltd | Sliding gate fabrication work | 95546.61 | 0 | 0 | 17198.3898 | 112744.9998 |  |  |  |  | 112745 | 112745 | -0.0002 | Submitted | 21.08.2025 | 25-2623 | 112745 |  |  | Original invoice submitted
10 | 21.08.2025 | PO | AGN/PO/M-018/2025-26 | 01.08.2025 | 074 - 2025-26 | Raga Glass Emporium | Supply and fixing of 12mm Glass | 32120.33 | 0 | 0 | 5781.6594 | 37901.9894 |  |  |  |  | 37902 | 37902 | -0.0106 | Submitted | 21.08.2025 | 94 | 31902 |  |  | Original invoice submitted
11 | 29.08.2025 | PO | AGN/PO/M-020/2025-26 | 29.08.2025 | 076 - 2025-26 | Mahavir Steel & Tubes | Supply of Steel | 71242.37 | 0 | 0 | 12823.6266 | 84065.9966 |  |  |  |  | 76818 | 76818 | 7247.9966 | Submitted | 30.08.2025 | 1220 | 76818 |  |  | Remainging balance received 7247.00 and Original invoice submitted - PO short closed
12 | 2025-09-16 | PO | AGN/PO/M-023/2025-26 | 16.09.2025 | 077 - 2025-26 | Aqualus water Solutions | Supply of Geo-Textile and HDPE Sheets | 29250 | 0 | 0 | 5265 | 34515 | 34515 |  |  |  |  | 34515 | 0 | Not Submitted | [5 empty] | 100% Advance as per client approval
13 | 09.10.2025 | PO | AGN/PO/M-025/2025-26 | 09.10.2025 | 086 - 2025-26 | BSA Steel Private Limited | Supply of Steel | 344067 | 0 | 0 | 61932.06 | 405999.06 |  |  |  |  | 413016 | 413016 | -7016.94 | Submitted | 10.10.2025 | BSA/03441/2526 | 413016 |  |  | Original invoice submitted - Qty.Excess as per the weigh so invoice value increased
14 | 2025-10-14 | PO | AGN/PO/M-025/2025-26 | 09.09.2025 | 087 - 2025-26 | Jain Metal | Supply of CC Sheets and Steel | 51035 | 0 | 0 | 9186.3 | 60221.3 | 60221 |  |  |  |  | 60221 | 0.3 | Not Submitted | [5 empty] | 100% Advance as per client approval
15 | 2025-11-18 | PO | AGN/PO/M-030/2025-26 | 2025-11-18 | 096 - 2025-26 | Jain Metal | Supply of Steel | 61494.91 | 0 | 0 | 11069.0838 | 72563.9938 | 72563.99 |  |  |  |  | 72563.99 | 0.0038 | Submitted | 18.11.2025 | INV/25-26/463 | 71520 |  |  | 100% Advance as per client approval
16 | 2025-11-19 | PO | AGN/PO/M-031/2025-26 | 2025-11-19 | 097 - 2025-26 | Deccan Wire Netting Works | Supply of Chain-link mesh | 62500 | 0 | 0 | 11250 | 73750 | 73750 |  |  |  |  | 73750 | 0 | Not Submitted | [5 empty] | 100% Advance as per client approval
17 | 2025-11-26 | PO | AGN/PO/M-032/2025-26 | 2025-11-26 | 099 - 2025-26 | Jain Metal | Supply of Steel | 160310 | 0 | 0 | 28855.8 | 189165.8 | 189166 |  |  |  |  | 189166 | -0.2 | Not Submitted | [5 empty] | 100% Advance as per client approval
18 | 28-11-2025 and 05.01.2026 | PO | AGN/PO/M-033/2025-26 | 2025-11-27 | 0101 - 2025-26 | Basant Florring Pvt Ltd | Supply of Shot blasted Square Pavers | 223250 | 0 | 0 | 40185 | 263435 | 131717.5 | 131717.5 |  |  |  | 263435 | 0 | Not Submitted | [5 empty] | 50% Advance as per client approval. Balance 50% paid
19 | 23-12-2025 and 20.01.2026 | PO | AGN/PO/M-038/2025-26 | 2025-12-22 | 0103 - 2025-26 | Classic Reflective Pavers | Supply of Grass Pavers | 105600 | 0 | 0 | 19008 | 124608 | 62304 | 62304 |  |  |  | 124608 | 0 | Not Submitted | [5 empty] | 50% Advance as per client approval & balance 50% paid as per clint approval
20 | 2026-01-09 | PO | AGN/PO/M-033/2025-26 | 2025-11-27 | 0101 - 2025-26 | Aditi Trans | Transport charges for Shot blasted Square Pavers | 52500 | 0 | 0 |  | 52500 | 52500 |  |  |  |  | 52500 | 0 | Not Submitted | [5 empty] | 100% Advance as per client approval
21 | 2026-01-20 | PO | AGN/PO/M-043/2025-26 | 2026-01-20 | 0114 - 2025-26 | Srinika Traders | Supply of Shera Pro Plain Boards | 41003.38 | 0 | 0 | 7380.6084 | 48383.9884 | 48384 |  |  |  |  | 48384 | -0.0116 | Not Submitted | [5 empty] | 100% Advance as per client approval
22 | 2026-01-31 | PO | AGN/PO/M-042/2025-26 | 2026-01-13 | 0111 - 2025-26 | Anjani Vishnu Allied Services Limited | Supply of Tiles | 76965.25 | 0 | 0 | 13853.745 | 90818.995 | 90819 |  |  |  |  | 90819 | -0.005 | Not Submitted | [5 empty] | 100% Advance as per client approval
23 | 2026-02-03 | PO | AGN/PO/M-045/2025-26 | 2026-02-03 | 0117 - 2025-26 | Jain Metal | Supply of Steel | 53111.01 | 0 | 0 | 9559.9818 | 62670.9918 | 62671 |  |  |  |  | 62671 | -0.0082 | Submitted | 03.02.2026 | INV/25-26/615 | 61100 |  |  | 100% Advance as per client approval
24 | 2026-02-05 | PO | AGN/PO/M-046/2025-26 | 2026-02-05 | 0120 - 2025-26 | OSB Prefab Technologies | Supply of Roof Panels with PPGI | 90920.33 | 0 | 0 | 16365.6594 | 107285.9894 | 53643 |  |  |  |  | 53643 | 53642.9894 | Not Submitted | [5 empty] | 50% Advance as per client approval
25 | 2026-02-06 | PO | AGN/PO/M-047/2025-26 | 2026-02-06 | 0120 - 2025-26 | Deccan Wire Netting Works | Supply of Chain-link mesh | 42000 | 0 | 0 | 7560 | 49560 | 49560 |  |  |  |  | 49560 | 0 | Not Submitted | [5 empty] | 100% Advance as per client approval
Grand Total | [11 empty] | 5399325.1614 | 3290824.99 | 1100060 | 0 | 0 | 954566 | 5345450.99 | 53874.1714 | 0 | 0 |  | 4685397.01

## WO_Payments
Invoice Tracker Work Order - 2025 to 2026
[13 empty] | Payment Details | [6 empty] | Invoice Status |  |  |  | UTR Details
S.No | Date | Order Type | Oder Ref No | Order Date | Budget No. | Supplier | Description | Order Value | Loading | Freight | Taxes | Total Amount | Advance 1 | Advance 2 | RA Bill 1 | RA Bill 2 | Final Bill | Total Paid | Balance to pay | Status | Date | Invoice No. | Amount | Date | UTR No. | Remarks
1 | 2025-04-29 | WO | AGN/WO/M-001/2025-26 | 2025-04-22 | 003 - 2024-25 | Robo Gates India Pvt Ltd | MS Showing Gate size 18.5ftx7ft | 100800 | - | - | 18144 | 118944 | 89208 |  |  |  |  | 89208 | 29736 | Not Submitted | [5 empty] | 75% Adavnec as per client approval
2 | 2025-06-02 | WO | AGN/WO/M-046/2024-25 | 2025-03-28 | 277 - 2024-25 | Jayadurga Furnishings Pvt Ltd | Supply and fixing of curtains | 625501 | - | - | 80362.66 | 705863.66 | 482351 |  |  |  | 223513 | 705864 | -0.34 | Submitted | 29.03.2025, 29.03.2025, 02.04.2025, 04.04.2025, 04.04.2025, 08.04.2025, 21.04.2025, 22.04.2025 and 28.04.2025 | SRV-24-25-624, SI-24-25-10714, SI-25-26-00051, SI-25-26-00108, SI-25-26-00116, SI-25-26-00203, SI-25-26-00487, SRV-25-26-83 and CS-25-26-342 | 49,570.00, 2360.00, 35599.00, 166359.00, 17916.00, 28763.00, 363171.00, 24780.00 and 17346.00 |  |  | All original invoices submitted with client sign
3 | 2025-06-12 | WO | AGN/WO/M-002/2025-26 | 2025-05-01 | 040 - 2024-25 | Mallick & Co | Plumbing Work | 504806.41 | - | - | 90865.1538 | 595671.5638 |  |  |  |  | 595672 | 595672 | -0.4362 | Submitted | 12.05.2025 | MC/25-26/013 | 595672 |  |  | Final Bill - Original invoice submitted with Madam Approval
4 | 2025-06-12 | WO | AGN/WO/M-003/2025-26 | 2025-05-05 | 041 - 2024-25 | Vishal Prajapathi | Labour charges for wooden Flooring polish work - Myna | 110390 | - | - |  | 110390 |  |  |  |  | 110390 | 110390 | 0 | Submitted | [5 empty] | Final Bill - Original non GST invoice submitted with Madam Approval
5 | 2025-06-17 | WO | AGN/WO/M-007/2025-26 | 2025-05-30 | 045 - 2025-26 | Mounika Construction | Lake side CRS work | 158250 |  |  | 28485 | 186735 |  |  |  |  | 186735 | 186735 | 0 | Submitted | 17.06.2025 | mou17/06/2025/02 | 186736 |  |  | All original invoices submitted with client sign
6 | 2025-06-17 | WO | AGN/WO/M-008/2025-26 | 2025-05-30 | 046 - 2025-26 | Mounika Construction | Lake side Retaing wall work | 1016495 |  |  | 182969.1 | 1199464.1 |  |  |  |  | 1199464.1 | 1199464.1 | 0 | Submitted | 17.06.2025 | mou17/06/2025 | 1199466 |  |  | All original invoices submitted with client sign
7 | 2025-06-17 | WO | AGN/WO/M-009/2025-26 | 2025-05-30 | 047 - 2025-26 | Mounika Construction | Civil Work | 168403.62 |  |  | 30312.6516 | 198716.2716 |  |  |  |  | 198716.27 | 198716.27 | 0.0016 | Submitted | 17.06.2025 | mou17/06/2025/03 | 198716 |  |  | All original invoices submitted with client sign
8 | 2025-08-14 | WO | AGN/WO/M-014/2025-26 | 2025-08-01 | 068 - 2025-26 | Little Twigs Studio | Architectural Advisary Service charges | 50000 |  |  | 9000 | 59000 |  |  |  |  | 59000 | 59000 | 0 | Submitted | 13.08.2025 | 6 | 59000 |  |  | All original invoices submitted
9 | 2025-08-18 | WO | AGN/WO/M-016/2025-26 | 2025-08-01 | 071 - 2025-26 | Mounika Construction | Civil Work | 946677.96 |  |  | 170402.0328 | 1117079.9928 |  |  |  |  | 1117080 | 1117080 | -0.0072 | Submitted | 2025-08-18 | mou18/08/2025 | 1117080 |  |  | Final Bill all original invoices submitted with client sign
10 | 2025-08-18 | WO | AGN/WO/M-015/2025-26 | 2025-08-01 | 070 - 2025-26 | Mounika Construction | Civil Work | 571605.93 |  |  | 102889.0674 | 674494.9974 |  |  |  |  | 674495 | 674495 | -0.0026 | Submitted | 2025-08-18 | mou18/08/2025/01 | 674495 |  |  | Final Bill all original invoices submitted with client sign
11 | 2025-09-18 | WO | AGN/WO/M-009/2024-25 | 2024-05-17 | 039 - 2024-25 | Go Infrastructures | Supply and fixing of Glass Windows | 1856776.27 |  |  | 334219.7286 | 2190995.9986 | 1533697.2 | 438198.9 |  |  | 131779.9 | 2103676 | Short Closed WO | Submitted | 11.08.2024 | GI/24-25/007 | 2190996 |  |  | Final Bill all original invoices submitted with client sign - Credit note of 87320.00 also submitted
12 | 2025-09-29 | WO | AGN/WO/M-019/2025-26 | 2025-08-01 | 080 - 2025-26 | Mounika Construction | Civil Work for Service Rooms and Main gate area | 449947.94 |  |  | 80990.6292 | 530938.5692 |  |  |  |  | 530939 | 530939 | -0.4308 | Submitted | 25.09.2025 | mou27/09/2025 | 530939 |  |  | Final Bill all original invoices submitted with client sign
13 | 29-09-2025 and 24.12.2025 | WO | AGN/WO/M-023/2025-26_Amended | 25-09-2025 and 24.12.2025 | 079 - 2025-26 | Mounika Construction | Civil Work for Dog Room and external works | 2529413.55 |  |  | 455294.439 | 2984707.989 | 300000 |  |  |  | 2684708 | 2984708 | -0.011 | Submitted | 24.12.2025 | mou24/12/2025 | 2984708 |  |  | Final Bill submitted with approval
14 | 2025-09-29 | WO | AGN/WO/M-001/2024-25 | 2025-04-03 | 001 - 2024-25 | Mounika Construction | Civil Work | 4737665.12 |  |  | 852779.7216 | 5590444.8416 | 4500000 |  |  |  | 548471 | 5048471 | 541973.8416 | Submitted | 25.09.2025 | mou25/09/2025 | 5048471 |  |  | Original Invoice submitted and WO short closed
15 | 2025-09-29 | WO | AGN/WO/M-020/2025-26 | 2025-09-02 | 081 - 2025-26 | M.N.V Building System | Supply and fabrication of steel | 87081 |  |  | 15674.58 | 102755.58 |  |  |  |  | 102756 | 102756 | -0.42 | Submitted | 29.09.2025 | MNV/25-26/113 | 102756 |  |  | Original Invoice submitted and WO short closed
16 | 2025-11-12 | WO | AGN/WO/M-027/2025-26 | 2025-11-11 | 094 - 2025-26 | Neptune Agri Solutions | SITC of Manual Irrigation works | 1376303 |  |  | 171802.09 | 1548105.09 | 309621.018 |  |  |  |  | 309621.018 | 1238484.072 | Not Submitted | [5 empty] | 20% Adavnec as per client approval
17 | 2025-11-13 | WO | AGN/WO/M-025/2025-26 | 2025-11-01 | 095 - 2025-26 | Little Twigs Studio | Architectural Advisary Service charges | 100000 |  |  | 18000 | 118000 |  |  |  |  | 118000 | 118000 | 0 | Submitted | 08.11.2025 | 7 | 118000 |  |  | All original invoices submitted
18 | 2025-11-24 | WO | AGN/WO/M-029/2025-26 | 2025-11-24 | 098 - 2025-26 | Classic Flooring &Interiors Pvt Ltd | Suuply and apply of Wooden Flooring | 219626.27 |  |  | 39532.7286 | 259158.9986 | 259159 |  |  |  |  | 259159 | -0.0014 | Not Submitted | [5 empty] | 100% Adavnec as per client approval
19 | 11/28/2025 and 19/02/2026 | WO | AGN/WO/M-029/2025-26 | 2025-11-27 | 0100 - 2025-26 | GSRK Tiles and Granites | Suuply and laying of Granite | 1768250 |  |  | 221045 | 1989295 | 599565 |  |  |  | 160629.74 | 760194.74 | 1229100.26 | Submitted | 13.02.2026 | GSRK-26-002 | 760194.74 |  |  | 60% Adavnec on supply amount as per client approval - Original Invoice Submitted
20 | 13-11-2025 and 30-12-2025 | WO |  | 2025-11-12 | 0106 - 2025-26 | Shiva Fabrication works | Fabrication work | 327123 |  |  |  | 327123 | 40000 |  |  | 0 | 287123 | 327123 | 0 | Submitted | 23.12.2025 | M-25-004 | 327123 |  |  | Final Bill
21 | 2026-02-03 | WO | AGN/WO/M-035/2025-26 | 2025-01-02 | 080 - 2025-26 | Mounika Construction | Civil Work for Compound wall | 2812362.71 |  |  | 506225.2878 | 3318587.9978 |  |  |  |  | 3318588 | 3318588 | -0.0022 | Submitted | 03.02.2026 | mou03/02/2026 | 3318588 |  |  | Final Bill all original invoices submitted with client sign
Grand Total | [11 empty] | 23926472.6504 | 8113601.218 | 438198.9 | 0 | 0 | 12248060.01 | 20799860.128 | 3039292.5238

## Direct_Payments
Invoice Tracker Direct Payments - 2024 to 2025
[10 empty] | Payment Details | [6 empty] | Invoice Status |  |  |  | UTR Details
S.No | Date | Budget No. | Supplier | Description | Order Value | Loading | Freight | Taxes | Total Amount | Advance 1 | Advance 2 | RA Bill 1 | RA Bill 2 | Final Bill | Total Paid | Balance to pay | Status | Date | Invoice No. | Amount | Date | UTR No. | Remarks
1 | 2025-04-12 | 004 - 2025-26 | Beyond Home Solutions Pvt Ltd | Supply of Ceiling Fans (M) | 24600 |  |  | 4428 | 29028 | 29028 |  |  |  |  | 29028 | 0 | Not Submitted | [5 empty] | 100% Advanec against client approval
2 | 2025-04-29 |  | Rao Enterprises | Supply of Pillows | 17416 |  |  | 3134.88 | 20550.88 |  |  |  |  | 20551 | 20551 | -0.12 | Submitted | 26.04.2025 | 2 | 20551 |  |  | Original invoice submitted with client approval
3 | 2025-05-13 | Open | Radha Krishna Granite & Tiles | Supply of Thandoor Stone | 24788.13 |  |  | 4461.8634 | 29249.9934 |  |  |  |  | 29250 | 29250 | -0.0066 | Submitted | 02.05.2025 amd 05.05.2025 | 5 and 6 | 29250 |  |  | Original invoice submitted with client approval
4 | 2025-05-13 | Open | Vijay Babu | Supply of River sand | 6332.5 |  |  |  | 6332.5 |  |  |  |  | 6332.5 | 6332.5 | 0 | Submitted | 28.04.2025 | 2 | 6332.5 |  |  | Original invoice submitted with client approval
5 | 2025-05-13 | Open | SN Infra | Supply of Cement | 2640 |  |  | 739.2 | 3379.2 |  |  |  |  | 3380 | 3380 | -0.8 | Submitted | 30.04.2025 | 265 | 3380 |  |  | Original invoice submitted with client approval
6 | 2025-05-13 | Open | Raju Enterprises | Supply of Stone Dust | 9000 |  |  |  | 9000 |  |  |  |  | 9000 | 9000 | 0 | Submitted | 04.05.2025 | 74 | 9000 |  |  | Original invoice submitted with client approval
7 | 2025-06-02 | Open | Radha Krishna Granite & Tiles | Supply of Polished Granite | 14691 |  |  | 2644.38 | 17335.38 |  |  |  |  | 17336 | 17336 | -0.62 | Submitted | 26.05.2025 | 12 | 17336 |  |  | Original invoice submitted with client approval
8 | 2025-07-02 | Open | Bhagya Laxmi Paint and Sanitary | Supply of Plumbing Materials | 38784.74 |  |  | 6981.2532 | 45765.9932 |  |  |  |  | 45766 | 45766 | -0.0068 | Submitted | 21.06.2025 | 1/130 | 45766 |  |  | Original invoice submitted with client approval
9 | 2025-07-02 | Open | Bhagya Laxmi Paint and Sanitary | Supply of Plumbing Materials | 22152.54 |  |  | 3987.4572 | 26139.9972 |  |  |  |  | 26140 | 26140 | -0.0028 | Submitted | 21.05.2025 | 1/085 | 26140 |  |  | Original invoice submitted with client approval
10 | 2025-07-02 | Open | Mayur Plywood & Electrical | Supply of Hardware and Electrical Materials | 22155.93 |  |  | 3988.0674 | 26143.9974 |  |  |  |  | 26144 | 26144 | -0.0026 | Submitted | 23.06.2025 and 24.06.2025 | 1974 and 1975 | 26144 |  |  | Original invoice submitted with client approval
11 | 2025-07-02 | Open | LGM Enterprises | Supply of Light Fittings | 5654.29 |  |  | 1017.7722 | 6672.0622 |  |  |  |  | 6672.9 | 6672.9 | -0.8378 | Submitted | 28.05.2025 | 216 | 6672.9 |  |  | Original invoice submitted with client approval
12 | 2025-07-02 | Open | SS Traders | Supply of Light Fittings | 14900 |  |  | 2682 | 17582 |  |  |  |  | 17582 | 17582 | 0 | Submitted | 23.06.2025 | 25-26/0021 | 17582 |  |  | Original invoice submitted with client approval
13 | 2025-07-02 | Open | Aslam Earth Movers | Supply of JCB and Tractrs on Hire Basis | 233500 |  |  |  | 233500 |  |  |  |  | 233500 | 233500 | 0 | Submitted | 22.06.2025 | 250 | 233500 |  |  | Original invoice submitted with client approval
14 | 2025-08-18 | Open | Aslam Earth Movers | Supply of JCB and Tractrs on Hire Basis | 120700 |  |  |  | 120700 |  |  |  |  | 120700 | 120700 | 0 | Submitted | 13.08.2025 | 258 | 120700 |  |  | Original invoice submitted with client approval
15 | 2025-08-18 | Open | SMR Earth Movers | Supply of Murrum | 25500 |  |  |  | 25500 |  |  |  |  | 25500 | 25500 | 0 | Submitted | 10.08.2025 | 3 | 25500 |  |  | Original invoice submitted with client approval
16 | 2025-08-18 | Open | Gopal Earth Movers | Supply of Murrum | 147500 |  |  |  | 147500 |  |  |  |  | 147500 | 147500 | 0 | Submitted | 07.08.2025 | 56 | 147500 |  |  | Original invoice submitted with client approval
17 | 2025-08-18 | Open | Saidulu Earth Movers | Supply of Murrum | 80100 |  |  |  | 80100 |  |  |  |  | 80100 | 80100 | 0 | Submitted | 13.08.2025 | 15 | 80100 |  |  | Original invoice submitted with client approval
18 | 25.08.2025 | 072 - 2025-26 | Chabildas Manikdas & Bro | Supply of Plumbing Materials | 34054.23 |  |  | 6129.7614 | 40183.9914 |  |  |  |  | 40184 | 40184 | -0.0086 | Submitted | 31.07.2025 | JH482 | 40184 |  |  | Original invoice submitted with client approval
19 | 2025-09-02 | Open | SMR Earth Movers | Supply of Murrum | 158600 |  |  |  | 158600 |  |  |  |  | 158600 | 158600 | 0 | Submitted | 01.09.2025 | 4 | 158600 |  |  | Original invoice submitted with client approval
20 | 2025-09-02 | Open | R.K Ceramics | Supply of Vetrified Tiles | 25200 |  |  | 4536 | 29736 |  |  |  |  | 29736 | 29736 | 0 | Submitted | 28.08.2025 | 59 | 29736 |  |  | Original invoice submitted with client approval
21 | 2025-10-14 | Open | Aslam Earth Movers | Supply of JCB and Tractrs on Hire Basis | 107650 |  |  |  | 107650 |  |  |  |  | 107650 | 107650 | 0 | Submitted |  |  | 107650 |  |  | Original invoice submitted with client approval
22 | 2025-10-14 | Open | SMR Earth Movers | Supply of JCB | 23400 |  |  |  | 23400 |  |  |  |  | 23400 | 23400 | 0 | Submitted |  |  | 23400 |  |  | Original invoice submitted with client approval
23 | 2025-10-14 | Open | YP Stone | Supply of Lime stone chips | 29893.5 |  |  |  | 29893.5 |  |  |  |  | 29893.5 | 29893.5 | 0 | Submitted |  |  | 29893.5 |  |  | Original invoice submitted with client approval
24 | 2025-10-14 | Open | Royal Glass & UPVC works | Supply of UPVC windows | 11434 |  |  |  | 11434 |  |  |  |  | 11434 | 11434 | 0 | Submitted |  |  | 11434 |  |  | Original invoice submitted with client approval
25 | 2025-10-14 | Open | Sudhakar Dharavath | Supply of labour | 29250 |  |  |  | 29250 |  |  |  |  | 29250 | 29250 | 0 | Submitted |  |  | 29250 |  |  | Original invoice submitted with client approval
26 | 2025-10-14 | Open | Raju Enterprises | Supply of dust | 40690 |  |  |  | 40690 |  |  |  |  | 40690 | 40690 | 0 | Submitted |  |  | 40690 |  |  | Original invoice submitted with client approval - Bank details not submitted
27 | 2025-11-03 | Open | SMR Earth Movers | Supply of JCB | 54600 |  |  |  | 54600 |  |  |  |  | 54600 | 54600 | 0 | Submitted | 26.10.2025 | 6 | 54600 |  |  | Original invoice submitted with client approval
28 | 2025-11-03 | Open | Sudhakar Dharavath | Supply of labour | 11300 |  |  |  | 11300 |  |  |  |  | 11300 | 11300 | 0 | Submitted | 27.10.2025 | 2 | 11300 |  |  | Original invoice submitted with client approval
29 | 2025-11-03 | Open | Aslam Earth Movers | Supply of JCB and Tractrs on Hire Basis | 62750 |  |  |  | 62750 |  |  |  |  | 62750 | 62750 | 0 | Submitted | 27.10.2025 | 260 | 62750 |  |  | Original invoice submitted with client approval
30 | 2025-11-03 | Open | Bhagya Laxmi Paint and Sanitary | Supply of Plumbing Materials | 63681 |  |  |  | 63681 |  |  |  |  | 63681 | 63681 | 0 | Submitted | 24.09.25, 27.09.25, 26.09.25, 24.09.25 and 22.09/25 | 1/304, 310,311, 314,318. 319 and 320 | 63681 |  |  | Original invoice submitted with client approval
31 | 2025-11-03 | Open | Mayur Plywood & Electrical | Supply of Hardware and Electrical Materials | 83417 |  |  |  | 83417 |  |  |  |  | 83417 | 83417 | 0 | Submitted | 5/9/25, 4/9/25, 1/9/25, 9/10/25 and 4/6/25 | 1931, 2138, 2139, 2147, 2148, 2149 and 2221 | 83417 |  |  | Original invoice submitted with client approval
32 | 2025-12-30 | Open | Aslam Earth Movers | Supply of JCB and Tractrs on Hire Basis | 90000 |  |  |  | 90000 |  |  |  |  | 90000 | 90000 | 0 | Submitted | 27.12.2025 | M-25-002 | 90000 |  |  | Original invoice submitted with client approval
33 | 2025-12-30 | Open | Sudhakar Dharavath | Supply of labour | 16190 |  |  |  | 16190 |  |  |  |  | 16190 | 16190 | 0 | Submitted | 27.12.2025 | M-25-005 | 16190 |  |  | Original invoice submitted with client approval
34 | 2025-12-30 | Open | Raju Enterprises | Supply of dust and JCB and Tractrs on Hire Basis | 156892 |  |  |  | 156892 |  |  |  |  | 156892 | 156892 | 0 | Submitted | 27.12.2025 | M-25-003 | 156892 |  |  | Original invoice submitted with client approval - Bank details not submitted
35 | 2025-12-30 | Open | Vijay Babu | Supply of River sand | 10204 |  |  |  | 10204 |  |  |  |  | 10204 | 10204 | 0 | Submitted | 27.12.2025 | 15 | 10204 |  |  | Original invoice submitted with client approval
36 | 2025-12-30 | Open | SMR Earth Movers | Supply of Murrum | 301600 |  |  |  | 301600 |  |  |  |  | 301600 | 301600 | 0 | Submitted | 27.12.2025 | M-25-004 | 301600 |  |  | Original invoice submitted with client approval
37 | 2026-02-18 | Open | Khaja Moin | Supply of Murrum | 114400 |  |  |  | 114400 |  |  |  |  | 114400 | 114400 | 0 | Submitted | 12.02.2026 | SMR-26-005 | 114400 |  |  | Original invoice submitted with client approval
38 | 2026-02-18 | Open | Manne Raju | Supply of Robo Sand and JCB | 145035 |  |  |  | 145035 |  |  |  |  | 145035 | 145035 | 0 | Submitted | 13.02.2026 | M-R-26-003 | 145035 |  |  | Original invoice submitted with client approval
39 | 2026-02-18 | Open | Chipuri Gopal | Supply of Murrum | 54600 |  |  |  | 54600 |  |  |  |  | 54600 | 54600 | 0 | Submitted | 11.02.2026 | M-CNY-26-008 | 54600 |  |  | Original invoice submitted with client approval
40 | 2026-02-18 | Open | Ganesh Kumar | Granite Laying Work | 251938 |  |  |  | 251938 |  |  |  |  | 251938 | 251938 | 0 | Submitted | 13.02.2026 | M-G-26-003 | 251938 |  |  | Original invoice submitted with client approval
0
Grand Total | [8 empty] | 2731924.4948 | 29028 | 0 | 0 | 0 | 2702898.9 | 2731926.9 | -2.4052